ATHERIS LIMITED

GRC WEBSITE

Implementation Plan & Project Roadmap

Version 1.0  |  March 2026

# 1. Project Overview

This Implementation Plan defines the full delivery roadmap for the Atheris Limited GRC platform website — a Laravel + Next.js headless CMS system. The plan spans 16 weeks from kickoff to production launch, organized into 5 phases.

| Attribute | Detail |
| --- | --- |
| Project Name | Atheris GRC Platform Website |
| Duration | 16 Weeks (4 Months) |
| Team Size | 7-10 People |
| Primary Stack | Laravel 11, Next.js 14, MySQL, Redis, AWS |
| Launch Target | July 2026 |
| Budget Category | Enterprise Web Development |

# 2. Team Structure

| Role | Count | Responsibilities |
| --- | --- | --- |
| Project Manager | 1 | Timeline, stakeholder comm, risk management, sprint planning |
| UI/UX Designer | 1-2 | Figma designs, design system, prototype, user testing |
| Frontend Engineer (React/Next.js) | 2 | All public pages, CMS admin UI, component library, animations |
| Backend Engineer (Laravel) | 2 | API development, CMS engine, auth, database, integrations |
| DevOps Engineer | 1 | AWS setup, CI/CD pipeline, Docker, monitoring, SSL |
| QA Engineer | 1 | Test plans, manual testing, automated E2E tests (Playwright) |
| Content Strategist | 1 | Website copy, solution page content, SEO content plan |

# 3. Phase Plan

## Phase 1: Foundation & Design (Weeks 1-3)

| Week | Deliverable | Owner | Status |
| --- | --- | --- | --- |
| Week 1 | Project kickoff, team onboarding, tool setup (Jira, Figma, GitHub, Slack) | PM | Planned |
| Week 1 | AWS infrastructure provisioning: VPC, RDS, ElastiCache, S3, CloudFront | DevOps | Planned |
| Week 1 | Laravel project init, base architecture, Sanctum auth, RBAC setup | Backend | Planned |
| Week 1 | Next.js project init, Tailwind config, base component scaffolding | Frontend | Planned |
| Week 2 | Figma design system: colors, typography, components, icons | UI/UX | Planned |
| Week 2 | Wireframes: Homepage, Solution pages (x6), Pricing, Demo request | UI/UX | Planned |
| Week 2 | Database schema design, migration files, model setup | Backend | Planned |
| Week 3 | High-fidelity designs: Homepage, Navigation, Footer, Blog layout | UI/UX | Planned |
| Week 3 | CI/CD pipeline setup: GitHub Actions, staging + production environments | DevOps | Planned |
| Week 3 | Design review and stakeholder sign-off on visual direction | PM + All | Planned |

## Phase 2: Core Development (Weeks 4-8)

| Week | Deliverable | Owner |
| --- | --- | --- |
| Week 4 | CMS content models and migrations, admin auth, media upload to S3 | Backend |
| Week 4 | Public API endpoints: pages, posts, resources, navigation, settings | Backend |
| Week 4 | Homepage development: hero, platform overview, stats, testimonials, CTA | Frontend |
| Week 5 | Solution pages template (x1 built, x5 replicated): all sections | Frontend |
| Week 5 | Blog listing, blog post detail, search and filter functionality | Frontend |
| Week 5 | CMS admin: post/page editor with TipTap rich text, media library | Frontend + Backend |
| Week 6 | Pricing page, ROI calculator interactive widget | Frontend |
| Week 6 | Demo request multi-step form + Calendly integration | Frontend + Backend |
| Week 6 | Customer stories listing and detail pages | Frontend |
| Week 7 | Resources hub: whitepaper listing, gated download flow, webinar embeds | Frontend + Backend |
| Week 7 | Platform overview, AI intelligence, security/trust pages | Frontend |
| Week 7 | Why Atheris pages: vs. Diligent, vs. Archer, ROI calculator backend | Frontend |
| Week 8 | CMS admin: full CRUD for all content types, settings manager | Frontend + Backend |
| Week 8 | Navigation manager in CMS (edit mega-menu structure) | Frontend + Backend |
| Week 8 | Lead capture API, HubSpot CRM webhook integration | Backend |

## Phase 3: Integration & Polish (Weeks 9-11)

| Week | Deliverable | Owner |
| --- | --- | --- |
| Week 9 | SEO: dynamic sitemaps, robots.txt, meta tags, Schema.org JSON-LD | Frontend + Backend |
| Week 9 | Google Analytics 4 + GTM setup, LinkedIn Insight Tag, Meta Pixel | Frontend + DevOps |
| Week 9 | Intercom live chat integration, Mailgun transactional emails | Backend |
| Week 10 | Animation polish: Framer Motion page transitions, scroll animations | Frontend |
| Week 10 | Mobile responsiveness audit and fixes across all pages | Frontend |
| Week 10 | Accessibility audit: keyboard nav, ARIA, contrast, screen reader test | Frontend + QA |
| Week 11 | Performance optimization: image opt, lazy loading, caching, Lighthouse | Frontend + DevOps |
| Week 11 | Security hardening: CSP headers, rate limiting, 2FA admin, OWASP scan | DevOps + Backend |
| Week 11 | Cookie consent banner (NDPA 2023 compliant) + Privacy policy pages | Frontend + Legal |

## Phase 4: Testing & QA (Weeks 12-14)

| Test Type | Scope | Tool | Owner |
| --- | --- | --- | --- |
| Functional Testing | All 30+ pages, forms, CMS CRUD, API endpoints | Manual + Postman | QA |
| Cross-browser Testing | Chrome, Firefox, Safari, Edge (latest 2 versions) | BrowserStack | QA |
| Mobile Testing | iOS 16+, Android 12+ — iPhone 14, Samsung Galaxy S23 | BrowserStack | QA |
| Performance Testing | Lighthouse, Core Web Vitals — all key pages | Lighthouse CI | Frontend + DevOps |
| Security Testing | OWASP ZAP automated scan, manual pen test of admin | OWASP ZAP | DevOps |
| Accessibility Testing | WCAG 2.1 AA audit on homepage + all template pages | axe DevTools | Frontend + QA |
| E2E Testing | Demo request flow, gated download, CMS publish workflow | Playwright | QA |
| Load Testing | Simulate 500 concurrent users, API response under load | k6 | DevOps |
| Content Review | All copy proofread, links checked, SEO meta validated | Screaming Frog | Content |
| UAT | Stakeholder review of all pages — sign-off required | Manual | PM + Client |

## Phase 5: Launch & Stabilization (Weeks 15-16)

| Task | Owner | Notes |
| --- | --- | --- |
| DNS cutover and SSL certificate activation | DevOps | Zero-downtime switch |
| Production deployment and smoke testing | DevOps + QA | Full regression check |
| Google Search Console submission + sitemap ping | Frontend | SEO indexing kickoff |
| CMS user training for content team (2hr session) | PM + Frontend | Recording provided |
| Analytics verification: GA4, GTM, CRM events | Frontend | Data layer test |
| Launch announcement: LinkedIn, press release, email | Marketing | Coordinate timing |
| Post-launch monitoring: 48hr war room | All Tech | Sentry + Datadog alerts |
| Week 16: Bug fixing, performance tuning, content updates | Frontend + Backend | Sprint 1 post-launch |
| Handover documentation and runbook | All Tech | Confluence/Notion |

# 4. Sprint Plan (2-Week Sprints)

| Sprint | Weeks | Goal | Key Deliverables |
| --- | --- | --- | --- |
| Sprint 1 | 1-2 | Foundation | Infrastructure, design system, wireframes, base architecture |
| Sprint 2 | 3-4 | Core design + CMS engine | HiFi designs, CMS backend, base APIs |
| Sprint 3 | 5-6 | Homepage + Solution pages | All 6 solution pages, homepage live on staging |
| Sprint 4 | 7-8 | Content hub + Pricing | Blog, resources, pricing, demo request, admin CMS |
| Sprint 5 | 9-10 | Integration + Polish | SEO, analytics, animations, mobile, accessibility |
| Sprint 6 | 11-12 | Security + QA | Performance, security hardening, functional testing |
| Sprint 7 | 13-14 | UAT + Final fixes | Stakeholder UAT, bug fixes, load testing |
| Sprint 8 | 15-16 | Launch + Stabilize | Production go-live, monitoring, handover |

# 5. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Content delays (copywriting not ready) | High | Medium | Start content brief in Week 1; use placeholder content to unblock dev |
| Design revision cycles extending timeline | Medium | High | Hard sign-off on wireframes before HiFi; 2 revision rounds max |
| AWS Lagos region latency issues | Low | High | Test with Bunny CDN African PoPs; fallback to CloudFront |
| Third-party integration failures (HubSpot, Calendly) | Low | Medium | Build abstraction layer; swap vendors without code changes |
| NDPA compliance gaps in data handling | Medium | High | Legal review in Week 10; Data Protection Officer sign-off |
| Key developer unavailability (illness/attrition) | Medium | High | Pair programming on critical paths; documentation-first culture |
| SEO indexing delays post-launch | Medium | Low | Submit sitemap pre-launch; enable ISR on day-1 |

# 6. Definition of Done

## Feature-Level DoD

- Code reviewed and approved by 1+ team member

- Unit tests written and passing (>80% coverage on backend)

- Responsive on mobile, tablet, desktop (320px to 1920px)

- Cross-browser tested (Chrome, Safari, Firefox)

- Accessibility checked (axe DevTools — zero critical errors)

- Performance budget met (LCP < 2.5s on 4G mobile)

- Deployed to staging and smoke tested

## Launch-Level DoD

- All UAT sign-offs received from stakeholders

- Lighthouse Performance > 90 on all key pages

- Zero P1/P2 bugs open

- NDPA compliance review completed and signed off

- Analytics tracking verified end-to-end

- CMS training completed for content team

- Runbook and documentation complete

- Monitoring and alerting configured and tested